## Sheet1
Issue # | Task Title/User stories | Story Points | Due Dates | Task Description | Priority | Risk | Risk explanation | Responsible
1 | Sprint 1: README file | 1 | 2024-09-29 | Create and complete the repository's README File | High | Low | Would be crazy to break something with this | Haichuan, Jeffrey
2 | Sprint 1: User can enter username and password to log in | 4 | 2024-09-29 | Create Welcome page. Create login page, add log in window to fill log in informations. Create account database. Link frontend and backend | High | Medium | Databse being manipulated, but not high risk as this is the first step of development, so nothing to break | Haichuan, Jeffrey
3 | Sprint 1: User can create teams and assign students to specific groups | 4 | 2024-09-29 | Build functionality for users to create teams and assign students to groups. | High | Medium | Database being manipulated | Jeremie, Ayman
4 | Sprint 1:Users should be visible to see teams | 2 | 2024-09-29 | Implement team visibility feature for users to view all teams and their members. | High | Medium | Database being manipulated | Jeremie, Ayman
5 | Sprint 1: Users should be able to choose from Instructor or Student Login | 1 | 2024-09-29 | Create buttons for seperate logins. Create pages for seperate logins. | High | Low | No data is being modified | Varun, Francois
6 | Sprint 1: User can create password when creating an account | 2 | 2024-09-29 | Create page for first time logins to create password. | High | Medium | Password creation might lock out users if forgotten password or typo | Varun, Francois
7 | Sprint 1: User can logout | 1 | 2024-09-29 | Create logout button | Medium | Low | Simply a button to redirect | Varun, Francois
8 | Sprint 1: User can change password | 2 | 2024-09-29 | Create button and page to change user password. | Low | High | Potential to ruin password fields | Varun, Francois
9 | Sprint 1: User can click on another student's name to bring the user to that student's profile | 2 | 2024-09-29 | Add a direct link that brings the user to a student profile: | Low | Low | Redirection link | Jeremie, Ayman
42 | Sprint 2: As a student, I want to be able to leave a review for my teamates. | 5 | 2024-10-18 | Tasks: - Add form for students to write reviews in the Frontend - Create webpage with the review form - Save reviews left by students in Backend - Student dashboard to see other team members | Medium | Low | If a problems arises with giving a review to a teamate, it will not affect any other page. Furthermore, there is currently no implementation that is dependant on the review system. | Haichuan, Francois
40 | Sprint 2: As an instructor, I want to be able to see all the teams and the students in them as well as a list of all the students with their corresponding team. | 9 | 2024-10-10 | Tasks: - Fetch a list of all students from database and display them with their team - Fetch a list of all the teams from data base and display them - Create webpage that displays the instructor's dashboard - In instructor's dashboard, add a search bar to search for specific team - In instructor's dashboard, create a filter button that switches from a list of all the teams and all the students - As an instructor, I want to be able to create a new team and assign students to them | High | High | This page is very important since it’s the main page (dashboard) of the instructor. It’s the page that will connect all of the possible features of the instructor together. This means that if a problems arises with the main page for instructor, it will affect all the other components. Furthermore, this is a top priority since all components have to be connected to this page | Haichuan, Francois, Varun, Ayman, Hoang Vu, Jeremy
16 | Sprint 2: As an instructor, I want to be able to create a new team and assign students to them. | 7 | 2024-10-24 | Tasks - Create a webpage that allows instructors to create new teams and assign students to them - Save newly created teams in the database - In instructor's dashboard, add an option to create a new team - Add a button that will let the instructor add a student to a already created team | Medium | Medium | This is one of the main feature of the instructor. The risk is medium because creating a new team or assigning students to a team directly affects the main interface (dashboard) of the instructor. Having a problem with this part will have a small rippling effect of the main interface. Furthermore, since this is one of the main feature of an instructor, this user story should be done in the beggining of the sprint | Haichuan, Francois, Varun, Ayman, Hoang Vu
9 | Sprint 2: As an instructor, I want to import a list of students from a CSV file. | 4 | 2024-10-18 | Tasks - Validating imported CSV roster and creating teams based on its data - Create a page that allows instructors to lead a CSV file from their device | Medium | Low | Since there is already a main way to add team (Add team manually), using a CSV file to add a team is just a secondary method for doing an action. Only reason why this user story is medium priority is because it is one of the requirement for the Sprint 2. Furthermore, there is close to no risk in the implementation of this component, since as said before, there is already a feature that allows to add new teams. Error in the implementation of this part will barely affect the overall project | Hoang Vu, Ayman, Francois, Jeffrey, Jeremy
8 | Sprint 2: As an instructor, I can modify existing teams. | 4 | 2024-10-18 | Tasks - Add option to modify existing teams in instructor dashboard - Modify teams in the database according to changes made by instructor | Medium | Low | Modifying a team is one of the main feature that an instructor has access to. This is a feature that is displayed on the main page. Despite this, this feature has a low risk since there is no components that really depend on this feature. So, while it is a important feature to include in the project, there is no tasks that depend on it, lowering the risk of this user story | Haichuan, Varun, Francois
12 | as a user, I want to be able to log in as a student or as a instructor | 7 |  | Tasks - Create a welcome page | Medium | Low
9