## Sheet1
Issue # | Task Title/User stories | Story Points | Due Dates | Task Description | Priority | Risk | Risk explanation | Responsible
1 | README file | 1 | 2024-09-29 | Create and complete the repository's README File | High | Low | Would be crazy to break something with this | Haichuan, Jeffrey
2 | User can enter username and password to log in | 4 | 2024-09-29 | Create Welcome page. Create login page, add log in window to fill log in informations. Create account database. Link frontend and backend | High | Medium | Databse being manipulated, but not high risk as this is the first step of development, so nothing to break | Haichuan, Jeffrey
3 | User can create teams and assign students to specific groups | 4 | 2024-09-29 | Build functionality for users to create teams and assign students to groups. | High | Medium | Database being manipulated | Jeremie, Ayman
4 | Users should be visible to see teams | 2 | 2024-09-29 | Implement team visibility feature for users to view all teams and their members. | High | Medium | Database being manipulated | Jeremie, Ayman
5 | Users should be able to choose from Instructor or Student Login | 1 | 2024-09-29 | Create buttons for seperate logins. Create pages for seperate logins. | High | Low | No data is being modified | Varun, Francois
6 | User can create password when creating an account | 2 | 2024-09-29 | Create page for first time logins to create password. | High | Medium | Password creation might lock out users if forgotten password or typo | Varun, Francois
7 | User can logout | 1 | 2024-09-29 | Create logout button | Medium | Low | Simply a button to redirect | Varun, Francois
8 | User can change password | 2 | 2024-09-29 | Create button and page to change user password. | Low | High | Potential to ruin password fields | Varun, Francois
9 | User can click on another student's name to bring the user to that student's profile | 2 | 2024-09-29 | Add a direct link that brings the user to a student profile: | Low | Low | Redirection link | Jeremie, Ayman
10 | Automatic Student Team Assignment | 3 | 2024-09-30 | Develop feature for CSV upload and student profile creation: - Create a CSV upload form for instructors. - Parse CSV and extract student data. - Implement student profile creation in the database. - Handle errors for malformed files. - Update database schema for student profiles. - Test the CSV upload and profile creation process. | High | Medium | Potential file format issues with CSV upload | Hoang Vu, Francois
11 | Manual Student Team Assignment | 5 | 2024-10-02 | Design the team assignment UI. Implement drag-and-drop for assigning students to teams. Build backend to update team assignments. Provide real-time team updates. Validate and prevent duplicate team assignments. Test the team assignment functionality. | Medium | High | Complex logic for team assignment, prone to bugs | Haichuan, Francois, Hoang Vu
12 | View All Teams Dashboard | 4 | 2024-10-04 | Design and implement the team dashboard UI. Add filtering/sorting functionality. Build backend service to fetch and display teams. Implement pagination for large teams. Test team display and filtering. | High | Low | Minimal risk; mainly UI design | Haichuan, Francois, Hoang Vu
13 | Reassign Students Between Teams | 3 | 2024-10-06 | Add drag-and-drop or dropdown for reassigning students. Build backend logic to update team assignments. Ensure database integrity during reassignment. Implement real-time updates for reassigned students. Test the reassignment functionality. | Medium | Medium | Possibility of incorrect reassignment logic | Haichuan, Francois, Hoang Vu
14 | Download Team Assignments | 2 | 2024-10-08 | Add a "Download CSV" button. Implement backend service to generate a CSV file. Ensure proper CSV formatting and validation. Provide error handling for download issues. Test the CSV download process. | Low | Low | Straightforward implementation | Hoang Vu, Francois
15 | As a team, we can finalize user stories | 2 | 2024-10-10 | Define and finalize user stories for Sprint 2 features and add them to GitHub | High | Low | Essential planning step; low risk of misalignment | Hoang Vu, Jeffrey
16 | As a team, we can decompose tasks and assign them | 3 | 2024-10-11 | Break down user stories into tasks, assign tasks based on expertise | High | Medium | Misaligned task allocation could cause delays | Hoang Vu
17 | As a team, we can create acceptance tests for Sprint 1 | 2 | 2024-10-12 | Develop acceptance tests for Sprint 1 features and link to relevant stories/tasks | Medium | Low | Ensures Sprint 1 features are thoroughly tested | Hoang Vu
18 | Instructors can see teams’ assignments | 4 | 2024-10-15 | Implement feature allowing both students and instructors to view team assignments | High | Medium | Database manipulation required, moderate risk | Varun, Francois
19 | Instructors can upload team rosters via CSV | 5 | 2024-10-15 | Build functionality to enable instructors to upload rosters via CSV | High | High | Potential file format or validation issues | jefrey, Varun
20 | Students can select teammates for evaluation | 3 | 2024-10-17 | Create intuitive UI for students to select teammates for peer evaluation | High | Low | Low risk due to simple UI design requirements | Jeremie, Ayman
21 | Students can submit selected teammate evaluations | 5 | 2024-10-20 | Develop backend and frontend logic to allow students to select teammates for evaluation | High | Low | Potential integration challenges | Haichuan, Francois
22 | Students can rate teammates on a 5-point scale | 4 | 2024-10-18 | Create a 5-point rating system to allow students to rate teammates on “Cooperation” | High | Medium | Straightforward implementation; limited risks | Haichuan, Francois
23 | Students can confirm submission of peer assessment | 3 | 2024-10-18 | Design and implement a confirmation page post peer assessment submission | Medium | Low | Low risk; simple page to confirm submission | Jeremie, Ayman
24 | As a team, we can run automated tests with CI | 6 | 2024-10-20 | Configure GitHub Actions to automate builds and run tests for each commit | High | High | Potential integration and testing issues | Jeremie, Ayman
25 | Instructors and students can see additional assessment dimensions | 5 | 2024-10-22 | Begin implementing additional dimensions: Conceptual Contribution, Practical Contribution, Work Ethic | High | Medium | Complexity in integrating additional fields | Haichuan, Francois
26 | As a team, we can test all completed features | 4 | 2024-10-25 | Test all completed features against success criteria for functionality and reliability | High | Medium | Testing failures could delay finalization | Jeremie, Ayman
27 | As a team, we can finalize and upload meeting notes | 2 | 2024-10-25 | Record and upload meeting notes along with individual time logs for Sprint 2 | Medium | Low | Low risk; primarily a documentation task | jeffrey
28 | As a team, we can prepare for Sprint Review and Retrospective | 3 | 2024-10-27 | Prepare for Sprint Review and Retrospective; gather feedback and analyze team performance | Medium | Low | Low risk; primarily a team reflection activity | jeffrey
[5 empty] | Medium | Low
[5 empty] | Medium | Low
[5 empty] | Medium | Low
[5 empty] | Medium | Low
[5 empty] | Medium | Low
[5 empty] | Medium | Low
[5 empty] | Medium | Low